## Sort
5S Implementation Guide and Check sheet
| Implementation Plan for Store | Status
1 | Cover Raw Material, WIP, Products – Finished Goods, Semi-finished goods, Idle Machines, Unwanted Tools, jigs, fixtures, Gage, Cupboards, Storage racks, desks, chairs, Papers, Titles, Activities, Reports, etc | Yes | Yes
2 | Plan for a roll out program for Red-Tagging |  | No
3 | Take a duration of 1- 2 weeks
4 | Agree on the criteria - Red Tag Criteria
5 | Print Red Tag Cards
6 | Decide on Red Tag Pile Area in each cell, unit and a special Red Tag Site in the plant
7 | Execute Red-Tagging Program
8 | Commence Red Tagging across the organization as per plan
9 | Involve a mix of people from different departments in red tagging
10 | Give minimum time to complete all the red tagging
11 | Move Red Tag items to Pile Area
12 | Conduct team huddles every day
13 | Evaluate Red Tagged Items and action immediately
14 | Compute financial value of the Red Tagged Items
15 | Make red tagging part of regular work responsibility of every role in the organization
16 | Conduct Red Tagging Event once in a while - Quarterly or Half-yearly, in addition to daily Red Tagging
All rights reserved. Copyright 2020 @ Canopus Business Management Group

## Store
5S Implementation Guide and Check sheet
| Implementation Plan for Store | Status
1 | Consider necessary items identified in Sort with regard to - Raw Material, WIP, Products – Finished Goods, Semi-finished goods, Machines, Tools & Gages |  | Yes
2 | For all necessary item that has to be retained, decided on the following: |  | No
3 | Where to store?
4 | Why to store there?
5 | What to store there?
6 | And how many?
7 | To decide on above 4 points, Keep in mind visibility, access and return as criteria.
8 | To implement the above use Signboards, Labeling, Color Coding, Contouring, as appropriate
9 | Develop consistent standards for signboards, labels, color coding and contouring across the organization
10 | Train all the employees on the new standards for replenishing or replacing items back
All rights reserved. Copyright 2020 @ Canopus Business Management Group

## Shine
5S Implementation Guide and Check sheet
| Implementation Plan for Shine | Status | Yes
1 | Perform first time cleaning after completion of Store or in parallel to eliminate obvious unclean areas |  | No
2 | Educate and communicate the importance of 'Shine' to every one
3 | Create list of unnecessary items for removal at each work station
4 | Create a list of locations to be cleaned daily by work station
5 | Establish garbage/scrap removal routines
6 | Establish what consumables are needed supplies and in what quantity and quality
7 | Teach how to perform cleaning (wherever required)
8 | Identify supervisor or manager to over see and routines to do so
9 | Establish above points as a cleaning checklist with calender
10 | Display the calender in each work station
11 | Perform above activities regularly
All rights reserved. Copyright 2020 @ Canopus Business Management Group

## Standardize
5S Implementation Guide and Check sheet
| Implementation Plan for Standardize | Status
1 | Establish Daily, Weekly and Monthly 5S responsibilities for each Cell, Unit and at Plant level - SOP to be documented and displayed at workplae |  | Yes
2 | Develop system that will enable anyone in the workplace to see problems when they occur |  | No
3 | Responsibilities to also include carrying out minor repairs and improvements
4 | SOPs to be visual as far as possible
5 | Integrate 5S responsibilities with Daily Work Management or other management practices, KRIs
6 | Allocate specific time for performing 5S after sufficient industrial engineering study - esp for Production staff
7 | Arrange for adequate suppliers of consumables for maintaining 'Shine'
8 | Extensively communicate the new standards to every person who is responsible
9 | Allow Flexibility to constantly challenge and improve first 3 Ss
All rights reserved. Copyright 2020 @ Canopus Business Management Group

## Sustain
5S Implementation Guide and Check sheet
| Implementation Plan for Sustain | Status
1 | 5S Audit Calender adherence |  | Yes
2 | QC Circles or Workplace improvement Kaizens |  | No
3 | Shop wise 5S Leaderboards
4 | Announcement and management of Reward and Recognition program
5 | 5S Photo Display and regular updates
6 | Conduct of 5S audit for cross functional leaders
7 | Provide feedback to facilities team for revision of design standards for upgradation or new facility design
8 | Plan half-yearly or yearly 5S Red Tag campaigns
9 | 5S champion rotation
All rights reserved. Copyright 2020 @ Canopus Business Management Group